## GanttChart
[SHOP FLOWERS] Project Schedule
[]
| Project Start Date |  | 2025-04-28 |  |  |  |  | Display Week | 1 | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8
| Project Lead | [8 empty] | 2025-04-28 | [6 empty] | 2025-05-05 | [6 empty] | 2025-05-12 | [6 empty] | 2025-05-19 | [6 empty] | 2025-05-26 | [6 empty] | 2025-06-02 | [6 empty] | 2025-06-09 | [6 empty] | 2025-06-16
 | time axis 2025-04-28 to 2025-06-22
WBS | TASK | Detail | PIC | PREDECESSOR | START | END | DAYS | % DONE | WORK DAYS | time axis 2025-04-28 to 2025-06-22
1 | STEP 1
1.1 | Setup Project Laravel | Setup project base: Laravel, admin template, login system. | DEV |  | 2025-04-28 | 2025-04-28 | 1 | 0% | 1
1.2 | CRUD Module Admin Panel | - Master produk (add, edit, delete) - Master kategori custom order - Data Customer - Setting payment gateway (Midtrans sandbox). - Setting Lokasi Penjemputan Barang | DEV |  | 2025-04-29 | 2025-05-04 | 6 | 0% | 4
2 | STEP 2
2.1 | Frontend Development | - Halaman form custom order - List produk & halaman detail produk - Integrasi form ke database. | DEV |  | 2025-05-05 | 2025-05-07 | 3 | 0% | 3
2.2 | Basic Cart System | - Simpan data order sementara. - Checkout redirect ke Midtrans. | DEV |  | 2025-05-08 | 2025-05-10 | 3 | 0% | 2
3 | STEP 3
3.1 | Integrasi Payment Midtrans | - Integrasi Snap API - Integrasi Payment status update ke database. | DEV |  | 2025-05-11 | 2025-05-13 | 3 | 0% | 2
4 | STEP 4
4.1 | Admin Order Management | - List semua order - Detail order + status pembayaran. | DEV |  | 2025-05-14 | 2025-05-18 | 5 | 0% | 3
4.2 | Admin Dashboard | - Dashboard Penjualan - Dashboard Customers | DEV |  | 2025-05-19 | 2025-05-21 | 3 | 0% | 3
4.3 | Admin Reporting | Module Report Penjualan - Report PDF - Report Excel | DEV |  | 2025-05-22 | 2025-05-23 | 2 | 0% | 2
4.4 | QA Testing & Bug Fix | Test flow end-to-end: order - bayar - update status. | DEV |  | 2025-05-24 | 2025-05-25 | 2 | 0% | 0
5 | STEP 5
5.1 | Deployment ke Live Server | Pindahkan ke domain yang asli. | DEV |  | 2025-05-26 | 2025-05-27 | 2 | 0% | 2
5.2 | Revisi Minor | Perbaikan berdasarkan feedback | DEV |  | 2025-05-28 | 2025-06-01 | 5 | 0% | 3
5.3 | [5 empty] | - | 0 | 0% | 0
Note on A7: Work Breakdown Structure Level 1: 1, 2, 3, ... Level 2: 1.1, 1.2, 1.3, ... Level 3: 1.1.1, 1.1.2, 1.1.3, … - The WBS uses a formula to control the numbering, but the formulas are different for different levels. Copy and Paste the cells in the WBS column from the examples at the bottom of the worksheet.
Note on B7: Task Description Enter the name of each task and sub-task. Use indents for sub-tasks.
Note on D7: Task Lead Enter the name of the Task Lead in this column.
Note on E7: Predecessor Tasks: You can use this column to enter the WBS of a predecessor for reference. The PRO version uses formulas to automatically calculate the Start Date based on the Predecessor.
Note on F7: Task Start Date You can manually enter the Start Date for each task or use a formula to create a dependency on a Predecessor. For example, you could enter =enddate+1 to set the Start date to the next calendar day, or =WORKDAY(enddate,1) to set the Start date to the next work day (excluding weekends), where enddate is the cell reference for the End date of the Predecessor task.
Note on G7: End Date: The End Date is calculated based on the Start Date and the Calendar Days columns.
Note on H7: Duration (Calendar Days) The duration is the number of calendar days for the given task. The duration is calculated as the End Date minus the Start Date plus 1 day, so that a task starting and ending on the same day has a duration of 1 day. Note: The conditional formatting used to create the gantt chart references this column.
Note on I7: Percent Complete Update the status of this task by entering the percent complete (between 0% and 100%).
Note on J7: Work Days Counts the number of work days, excluding the weekends (Saturday and Sunday). In the PRO version, you can customize the work week and list specific non-working days like holidays. In the PRO version, the default input is the Work Days instead of the Calendar Days.